## Sheet2
|  | CIP # |  |  | Date Updated
Project Name
Project Manager
Contract Specialist
Real Estate Manager
Shore
Division Chief
[7 empty] | Yes or No | Yes or No | Yes or No | Yes or No |  | Yes or No
CIP ID | Task# | Task Description | Phase | Design Status | Start Date | End Date | Interceptor Operations? | Treatment Operations? | Electrical Review? | Instrumentation Review? | Duration | Task Complete
0 | 1 | Notice to Proceed_PER | PER
0 | 2 | Project Kickoff | PER
0 | 3 | Technical Memorandum Preparation 1 | PER
0 | 4 | HRSD Review Period - Technical Memo Review 1 | PER
0 | 5 | Technical Memorandum Preparation 2 | PER
0 | 6 | HRSD Review Period - Technical Memo Review 2 | PER
0 | 7 | Draft PER Preparation | PER | Draft
0 | 8 | HRSD Review Period - Draft PER Review | PER | Draft
0 | 9 | Final PER Preparation and Submittal | PER | Final
0 | 10 | HRSD Review Period - Final PER Review | PER | Final
0 | 11 | Notice to Proceed_Design | Design
0 | 12 | Survey / SUE / Geotechnical | Design
0 | 13 | Design Submittal 1 Preparation | Design
0 | 14 | HRSD Review Period - Design Review 1 | Design
0 | 15 | Design Submittal 2 Preparation | Design
0 | 16 | HRSD Review Period - Design Review 2 | Design
0 | 17 | Design Submittal 3 Preparation | Design
0 | 18 | HRSD Review Period - Design Review 3 | Design
0 | 19 | Design Submittal 4 Preparation | Design
0 | 20 | HRSD Review Period - Design Review 4 | Design
0 | 21 | Design Submittal 5 Preparation | Design
0 | 22 | HRSD Review Period - Design Review 5 | Design
0 | 23 | Bid Ready Plan Submittal | Design
0 | 24 | Advertise for Construction Bids | Design
0 | 25 | Site Visit / Issue Addendum | Design
0 | 26 | Bid Opening | Design
0 | 27 | Evaluation of Bids | Design
0 | 28 | Commission Meeting | Design
0 | 29 | Issue Notice of Award | Design
0 | 30 | Pre-Construction Meeting | Construction
0 | 31 | Notice to Proceed_Construction | Construction
0 | 32 | Submittals Preparation, Review, Approval | Construction
0 | 33 | Material/Equipment Order and Delivery | Construction
0 | 34 | Mobilization / Site Clearing | Construction
0 | 35 | Site Work / Construction Activities | Construction
0 | 36 | HRSD Involvement with Start-up & Testing | Construction
0 | 37 | Construction Activities for Substantial Completion Milestone | Construction
0 | 38 | Substantial Completion Verifications (HRSD Assistance) | Construction
0 | 39 | Final Completion Verifications (HRSD Assistance) | Construction
0 | 40 | Project Closeout Stage | Construction
Formulas:
Yes or No = IF(ISBLANK(Table1[[#This Row],[End Date]]),"",IF(Table1[[#This Row],[End Date]]<TODAY(), "Yes","No"))
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Example: PER - Draft? Final? Design Reviews: 30%, 60%, 90%, 100%
Note on E22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update to appropriate design milestone. Examples: 30%, 60%, 90%, 100%, etc.
Note on E23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update to appropriate design milestone.
Note on E24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update to appropriate design milestone.
Note on E25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update to appropriate design milestone.
Note on E26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update to appropriate design milestone.
Note on E27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update to appropriate design milestone.
Note on E28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update to appropriate design milestone.
Note on E29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update to appropriate design milestone.
Note on E30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update to appropriate design milestone.
Note on E31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update to appropriate design milestone.

## Task Lookup
Notice to Proceed_PER | 1 | Project Manager | Contract Specialist | Real Estate Manager | Shore | Division Chief
Project Kickoff | 2 | Andy Nelson | Katrina Davis | Ayanna Williams | NS | Gary Hart
Technical Memorandum Preparation 1 | 3 | Angela Weatherhead | Rebecca Ashley | Karen Scarano | SS | Jeff Layne
HRSD Review Period - Technical Memo Review 1 | 4 | Ann Copeland | Shannon Rice | Kristen Wentworth | SCD - Middle Peninsula | Jeff Scarano
Technical Memorandum Preparation 2 | 5 | Beatriz Patino | Trisha Hartman | TBD | SCD - Surry | Lauren Luravnsky
HRSD Review Period - Technical Memo Review 2 | 6 | Becky Currall | TBD |  | SCD - Eastern Shore
Draft PER Preparation | 7 | Holly Anne Matel |  |  | General
HRSD Review Period - Draft PER Review | 8 | Laura Kirkwood
Final PER Preparation and Submittal | 9 | Nicholas Taschner
HRSD Review Period - Final PER Review | 10 | Phil Hubbard
Notice to Proceed_Design | 11 | Shirley Smith
Survey / SUE / Geotechnical | 12 | Ted Denny
Design Submittal 1 Preparation | 13 | Tim Marsh
HRSD Review Period - Design Review 1 | 14 | Virginia Opp
Design Submittal 2 Preparation | 15
HRSD Review Period - Design Review 2 | 16
Design Submittal 3 Preparation | 17
HRSD Review Period - Design Review 3 | 18
Design Submittal 4 Preparation | 19
HRSD Review Period - Design Review 4 | 20
Design Submittal 5 Preparation | 21
HRSD Review Period - Design Review 5 | 22
Bid Ready Plan Submittal | 23
Advertise for Construction Bids | 24
Site Visit / Issue Addendum | 25
Bid Opening | 26
Evaluation of Bids | 27
Commission Meeting | 28
Issue Notice of Award | 29
Pre-Construction Meeting | 30
Notice to Proceed_Construction | 31
Submittals Preparation, Review, Approval | 32
Material/Equipment Order and Delivery | 33
Mobilization / Site Clearing | 34
Site Work / Construction Activities | 35
HRSD Involvement with Start-up & Testing | 36
Construction Activities for Substantial Completion Milestone | 37
Substantial Completion Verifications (HRSD Assistance) | 38
Final Completion Verifications (HRSD Assistance) | 39
Project Closeout Stage | 40