## schedule
Attachment A: Anticipated Schedule from initial Investigation to General Permit Acquisition
Schedule of Events For CIP Dewatering Activities
Stage | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Project out to Bid | Month A |  |  |  | Month B |  |  |  | or until end of dewatering activities
| Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Perform CHMRS and/or Phase I ESA
Phase II ESA (sampling & analyses)
Treatment System Design
Apply For & Acquire VPDES Permit | [13 empty] | or until end of dewatering activities Week 1: Construction/Dewatering Activities Commence
Apply For & Acquire HRSD Permit | [13 empty] | or until end of dewatering activities Week 1: Construction/Dewatering Activities Commence
Order Groundwater Treatment System | bar: Month A Week 1 to Month A Week 2
System Delivery & Onsite Set-up (if req.) | bar: Month B Week 4
Inspection by HRSD personnel | bar: Month B Week 4
Activate Permit (HRSD/VDEQ) | bar: Month B Week 4
Dewatering Activities | bar: or until end of dewatering activities Week 1 to or until end of dewatering activities Week 4
Monthly VPDES Sampling and Reporting | bar: or until end of dewatering activities Week 3; or until end of dewatering activities Week 3
Weekly HRSD Sampling & Reporting | bar: or until end of dewatering activities Week 1 to or until end of dewatering activities Week 4
Deactivate Permit(s) (HRSD/VDEQ) | bar: or until end of dewatering activities Week 4