**Attachment A – Project Costs, Schedule, and Risks Report**

**CIP Baseline at Activity Start (June 1, 2015)**

**Capital Budget:**

|  |  |  |
| --- | --- | --- |
| Phase | Costs | Details |
| Pre-planning: | $142,885 | All project costs prior to start of PER. |
| PER: | $196,467 | Professional Services costs as well as all other PER phase costs |
| Design: | $375,073 | Professional Services costs, condition assessment, easements, as well as all other Design Phase costs |
| Pre-Construction: | $71,442 | Bid stage activities |
| Construction: | $5,715,400 | Includes CA/CI costs, construction contract, and all other construction phase costs |
|  |  |  |
| Estimated Program Cost: | $6,501,267 |  |
| Contingency (20%): | $1,143,080 | Contingency set at 20% |
| Estimated Project Cost: | $7,644,347 |  |

**Schedule:**

|  |  |  |
| --- | --- | --- |
| Phase | Schedule | Details |
| Pre-planning start: | June 2015 | 5-month duration |
| PER start: | November 2015 | 8-month duration |
| Design start: | July 2016 | 21-month duration |
| Pre-Construction start: | April 2018 | 4-month duration |
| Construction start: | August 2018 | 21-month duration |
| Project Completion: | May 2020 |  |

**Risk Assessment and Mitigation Discussion:**

|  |  |  |
| --- | --- | --- |
| Phase | Risk Assessment | Risk Mitigation Consideration |
| Pre-planning: | Professional Services Selection delayed from original schedule by 1 month. Likely impact to remainder of schedule. | Evaluate compressing PER or Design phase to account for lost time. |
| PER: |  |  |
| Design: |  |  |
| Pre-Construction: |  |  |
| Construction: |  |  |
| Project Completion: |  |  |

**Draft PER (February 15, 2016)**

**Updated Capital Budget:**

|  |  |  |  |
| --- | --- | --- | --- |
| Phase | Revised Costs | % Change from CIP Baseline | Details |
| Pre-planning: | $0 | -100% | Delta: -$142,885. The earlier anticipated costs for this phase were reassigned under Design. |
| PER: | $250,000 | +27% | Delta: +$53,533. Negotiated PER work including Additional Services for SUE and meetings with Virginia Beach, Norfolk, and other stakeholders. |
| Design: | $550,000 | +47% | Delta: +$174,927. Incorporation of additional pipe condition assessment and hydraulic modeling for alternate pipe diameters. |
| Pre-Construction: | $25,000 | -65%  | Delta: -$46,442. Closer estimate of costs to be expended during Construction bid and award stage. |
| Construction: | $7,000,000 | +20% | Delta: +$1,284,600. Complexity of construction along corridor and alternatives. |
|  |  |  |  |
| Estimated Program Cost: | $7,825,000 | +20% | Delta: +$1,323,733.  |
| Contingency (20%): | $1,565,000 | +37% | Delta: +$421,920. |
| Estimated Project Cost: | $9,393,000 | +23% | Delta: +$1,745,653. |

**Updated Schedule:**

|  |  |  |  |
| --- | --- | --- | --- |
| Phase | Revised Schedule | % Change from CIP Baseline | Details |
| Pre-planning start: | July 2015 | 0% | Delta: +1 month from baseline date. |
| PER start: | December 2015 | 0% | Delta: +1 month from baseline date. Same duration as baseline between pre-planning and PER start. |
| Design start: | August 2016 | 0% | Delta: +1 month from baseline date. Same duration as baseline for PER phase. |
| Pre-Construction start: | October 2017 | -28% | Delta: -6 months from baseline date. Duration reduced to 15 months from baseline duration of 21 months for Design phase to reach bid ready stage. |
| Construction start: | February 2018 | 0% | Delta: -6 months from baseline date. Same duration as baseline for pre-construction phase.  |
| Project Completion: | February 2020 | +14% | Delta: -3 months from baseline date. Duration is 3 months longer than the baseline Construction phase of 21 months due to constructability issues. |

**Risk Assessment and Mitigation Discussion:**

|  |  |  |
| --- | --- | --- |
| Phase | Risk Assessment | Risk Mitigation Consideration |
| Pre-planning: | Closed out |  |
| PER: | Several alternative routes identified in the PER that have higher projected construction costs and longer construction schedules as compared to the preliminary recommended route and pipe length. | Explore alternate construction means and methods to reduce cost. |
| Design: |  |  |
| Pre-Construction: |  |  |
| Construction: | Depending on the pipe alignment selected by HRSD, the construction could result in higher traffic disruption and therefore limited work hours / days by either Norfolk or Virginia Beach. | Coordinate with locality traffic maintenance group to clarify expectations and collaborate on construction duration reducing opportunities. |
| Project Completion: |  |  |

**Final PER (July 1, 2016)**

**Updated Capital Budget:**

|  |  |  |  |
| --- | --- | --- | --- |
| Phase | Revised Costs | % Change from CIP Baseline | Details |
| Pre-planning: | $0 | -100% | Delta: -$142,885. The earlier anticipated costs for this phase were reassigned under Design. |
| PER: | $250,000 | +27% | Delta: +$53,533. Negotiated PER work including Additional Services for SUE and meetings with Virginia Beach, Norfolk, and other stakeholders. |
| Design: | $550,000 | +47% | Delta: +$174,927. Incorporation of additional pipe condition assessment and hydraulic modeling for alternate pipe diameters. |
| Pre-Construction: | $25,000 | -65%  | Delta: -$46,442. Closer estimate of costs to be expended during Construction bid and award stage. |
| Construction: | $7,200,000 | +26% | Delta: +$1,484,600. A pipe alignment selected by HRSD from PER alternatives that added more length to avoid future O&M issues. |
|  |  |  |  |
| Estimated Program Cost: | $8,025,000 | +23% | Delta: +$1,523,733.  |
| Contingency (15%): | $1,203,750 | +5% | Delta: +$60,670. Contingency adjusted to 15%. |
| Estimated Project Cost: | $9,228,750 | +21% | Delta: +$1,584,403. |

**Updated Schedule:**

|  |  |  |  |
| --- | --- | --- | --- |
| Phase | Revised Schedule | % Change from CIP Baseline | Details |
| Pre-planning start: | July 2015 | 0% | Delta: +1 month from baseline date. |
| PER start: | December 2015 | 0% | Delta: +1 month from baseline date. Same duration as baseline between pre-planning and PER start. |
| Design start: | August 2016 | 0% | Delta: +1 month from baseline date. Same duration as baseline for PER phase. |
| Pre-Construction start: | October 2017 | -28% | Delta: -6 months from baseline date. Duration reduced to 15 months from baseline duration of 21 months for Design phase to reach bid ready stage. |
| Construction start: | February 2018 | 0% | Delta: -6 months from baseline date. Same duration as baseline for pre-construction phase.  |
| Project Completion: | February 2020 | +14% | Delta: -3 months from baseline date. Duration is 3 months longer than the baseline Construction phase of 21 months due to constructability concerns. |

**Risk Assessment and Mitigation Discussion:**

|  |  |  |
| --- | --- | --- |
| Phase | Risk Assessment | Risk Mitigation Consideration |
| Pre-planning: | Closed out |  |
| PER: | Closed out |  |
| Design: | The timing for construction of the new Outlet Mall and access road may create coordination issues and adjustments for the design phase. |  |
| Pre-Construction: |  |  |
| Construction: | The timing for construction of the new Outlet Mall and access road may create coordination issues and adjustments for the construction phase. Construction could result in higher traffic disruption and therefore limited work hours / days by either Norfolk or Virginia Beach. | Coordinate with Developer and Locality to clarify expectations and collaborate on construction duration reductions and ways to lessen anticipated disruptive construction impacts. |
| Project Completion: | Issues discussed above may delay project completion. |  |

**90% Design (August 1, 2017)**

**Updated Capital Budget:**

|  |  |  |  |
| --- | --- | --- | --- |
| Phase | Revised Costs | % Change from CIP Baseline | Details |
| Pre-planning: | $0 | -100% | Delta: -$142,885. The earlier anticipated costs for this phase were reassigned under Design. |
| PER: | $250,000 | +27% | Delta: +$53,533. Negotiated PER work including Additional Services for SUE and meetings with Virginia Beach, Norfolk, and other stakeholders. |
| Design: | $580,000 | +55% | Delta: +$204,927. Incorporation of additional pipe condition assessment, hydraulic modeling for alternate pipe diameters, detailed traffic maintenance plans for both Norfolk and Va Beach. |
| Pre-Construction: | $25,000 | -65%  | Delta: -$46,442. Closer estimate of costs to be expended during Construction bid and award stage. |
| Construction: | $7,200,000 | +26% | Delta: +$1,484,600. A pipe alignment selected by HRSD from PER alternatives that added more length to avoid future O&M issues. |
|  |  |  |  |
| Estimated Program Cost: | $8,055,000 | +24% | Delta: +$1,553,733.  |
| Contingency (10%): | $805,500 | -30% | Delta: -$337,580. Contingency adjusted to 10%. |
| Estimated Project Cost: | $8,860,500 | +16% | Delta: +$1,216,153. |

**Updated Schedule:**

|  |  |  |  |
| --- | --- | --- | --- |
| Phase | Revised Schedule | % Change from CIP Baseline | Details |
| Pre-planning start: | July 2015 | 0% | Delta: +1 month from baseline date. |
| PER start: | December 2015 | 0% | Delta: +1 month from baseline date. Same duration as baseline between pre-planning and PER start. |
| Design start: | August 2016 | 0% | Delta: +1 month from baseline date. Same duration as baseline for PER phase. |
| Pre-Construction start: | October 2017 | -24% | Delta: -5 months from baseline date. One month added to Design duration evaluated at Final PER for total of 16 months for additional review times for Norfolk and Virginia Beach. |
| Construction start: | March 2018 | 0% | Delta: -5 months from baseline date. Same duration as baseline for pre-construction phase.  |
| Project Completion: | March 2020 | +14% | Delta: -2 months from baseline date. Duration is 3 months longer than the baseline Construction phase of 21 months due to constructability concerns. |

**Risk Assessment and Mitigation Discussion:**

|  |  |  |
| --- | --- | --- |
| Phase | Risk Assessment | Risk Mitigation Consideration |
| Pre-planning: | Closed out |  |
| PER: | Closed out |  |
| Design: | Final review and approval by cities of Norfolk and Virginia Beach. | Clarify with locality the plan approval process. |
| Pre-Construction: |  |  |
| Construction: | The timing for construction of the new Outlet Mall and access road will create coordination issues during the construction phase if changes by either HRSD contractor or developer of outlet mall from current state. Construction could result in higher traffic disruption and therefore limited work hours / days by either Norfolk or Virginia Beach. | Consider frequent meetings between locality, developer team, and HRSD team to heighten opportunities for early knowledge of conflicting matters and schedules for collaboration decisions. |
| Project Completion: | Issues discussed above may delay project completion. |  |

**PreConstruction (October 1, 2017)**

**Updated Capital Budget:**

|  |  |  |  |
| --- | --- | --- | --- |
| Phase | Revised Costs | % Change from CIP Baseline | Details |
| Pre-planning: | $0 | -100% | Delta: -$142,885. The earlier anticipated costs for this phase were reassigned under Design. |
| PER: | $250,000 | +27% | Delta: +$53,533. Negotiated PER work including Additional Services for SUE and meetings with Virginia Beach, Norfolk, and other stakeholders. |
| Design: | $580,000 | +55% | Delta: +$204,927. Incorporation of additional pipe condition assessment, hydraulic modeling for alternate pipe diameters, detailed traffic maintenance plans for both Norfolk and VA Beach. |
| Pre-Construction: | $21,000 | -71%  | Delta: -$50,442. Actual expenditures. |
| Construction: | $7,003,000 | +23% | Delta: +$1,287,600. New figures based on OPCC and construction schedule. |
|  |  |  |  |
| Estimated Program Cost: | $7,854,000 | +20% | Delta: +$1,352,733.  |
| Contingency (5%): | $392,700 | -64% | Delta: -$750,380. Contingency adjusted to 5%. |
| Estimated Project Cost: | $8,246,700 | +8% | Delta: +$602,353. |

**Updated Schedule:**

|  |  |  |  |
| --- | --- | --- | --- |
| Phase | Revised Schedule | % Change from CIP Baseline | Details |
| Pre-planning start: | July 2015 | 0% | Delta: +1 month from baseline date. |
| PER start: | December 2015 | 0% | Delta: +1 month from baseline date. Same duration as baseline between pre-planning and PER start. |
| Design start: | August 2016 | 0% | Delta: +1 month from baseline date. Same duration as baseline for PER phase. |
| Pre-Construction start: | October 2017 | -24% | Delta: -5 months from baseline date. One month added to Design duration evaluated at Final PER for total of 16 months for additional review times for Norfolk and Virginia Beach. |
| Construction start: | March 2018 | 0% | Delta: -5 months from baseline date. Same duration as baseline for pre-construction phase.  |
| Project Completion: | December 2019 | +5% | Delta: -5 months from baseline date. Duration is 1 month longer than the baseline Construction phase of 21 months due to Bid Document allowable duration. |

**Risk Assessment and Mitigation Discussion:**

|  |  |  |
| --- | --- | --- |
| Phase | Risk Assessment | Risk Mitigation Consideration |
| Pre-planning: | Closed out |  |
| PER: | Closed out |  |
| Design: | Final review and approval by cities of Norfolk and Virginia Beach. | Clarify with locality the plan approval process. |
| Pre-Construction: |  |  |
| Construction: | The timing for construction of the new Outlet Mall and access road will create coordination issues during the construction phase if changes by either HRSD contractor or developer of outlet mall. Construction could result in higher traffic disruption and therefore limited work hours / days by either Norfolk or Virginia Beach. | Consider frequent meetings between locality, developer team, and HRSD team to heighten opportunities for early knowledge of conflicting matters and schedules for collaboration decisions. |
| Project Completion: | Issues discussed above may delay project completion. |  |

**Evaluation of Construction Bids (November 1, 2017)**

**Updated Capital Budget:**

|  |  |  |  |
| --- | --- | --- | --- |
| Phase | Revised Costs | % Change from CIP Baseline | Details |
| Pre-planning: | $0 | -100% | Delta: -$142,885. The earlier anticipated costs for this phase were reassigned under Design. |
| PER: | $250,000 | +27% | Delta: +$53,533. Negotiated PER work including Additional Services for SUE and meetings with Virginia Beach, Norfolk, and other stakeholders. |
| Design: | $580,000 | +55% | Delta: +$204,927. Incorporation of additional pipe condition assessment, hydraulic modeling for alternate pipe diameters, detailed traffic maintenance plans for both Norfolk and VA Beach. |
| Pre-Construction: | $21,000 | -71%  | Delta: -$50,442. Actual expenditures. |
| Construction: | $6,927,150 | +21% | Delta: +$1,211,750. Lowest responsible and responsive bid was less than OPCC. |
|  |  |  |  |
| Estimated Program Cost: | $7,778,150 | +20% | Delta: +$1,276,883.  |
| Contingency (5%): | $388,908 | -66% | Delta: -$754,172. Contingency held at 5%. |
| Estimated Project Cost: | $8,167,058 | +7% | Delta: +$522,711. |

**Updated Schedule:**

|  |  |  |  |
| --- | --- | --- | --- |
| Phase | Revised Schedule | % Change from CIP Baseline | Details |
| Pre-planning start: | July 2015 | 0% | Delta: +1 month from baseline date. |
| PER start: | December 2015 | 0% | Delta: +1 month from baseline date. Same duration as baseline between pre-planning and PER start. |
| Design start: | August 2016 | 0% | Delta: +1 month from baseline date. Same duration as baseline for PER phase. |
| Pre-Construction start: | October 2017 | -24% | Delta: -5 months from baseline date. One month added to Design duration evaluated at Final PER for total of 16 months for additional review times for Norfolk and Virginia Beach. |
| Construction start: | March 2018 | 0% | Delta: -5 months from baseline date. Same duration as baseline for pre-construction phase.  |
| Project Completion: | December 2019 | +5% | Delta: -5 months from baseline date. Duration is 1 month longer than the baseline Construction phase of 21 months due to Bid Document allowable duration. |

**Risk Assessment and Mitigation Discussion:**

|  |  |  |
| --- | --- | --- |
| Phase | Risk Assessment | Risk Mitigation Consideration |
| Pre-planning: | Closed out |  |
| PER: | Closed out |  |
| Design: | Closed out |  |
| Pre-Construction: | Closed out |  |
| Construction: | The timing for construction of the new Outlet Mall and access road will create coordination issues during the construction phase if changes by either HRSD contractor or developer of outlet mall. Construction could result in higher traffic disruption and therefore limited work hours / days by either Norfolk or Virginia Beach. | Consider frequent meetings between locality, developer team, and HRSD team to heighten opportunities for early knowledge of conflicting matters and schedules for collaboration decisions. |
| Project Completion: | Issues discussed above may delay project completion. |  |

**Mid Point of Construction (January 1, 2019)**

**Updated Capital Budget:**

|  |  |  |  |
| --- | --- | --- | --- |
| Phase | Revised Costs | % Change from CIP Baseline | Details |
| Pre-planning: | $0 | -100% | Delta: -$142,885. The earlier anticipated costs for this phase were reassigned under Design. |
| PER: | $250,000 | +27% | Delta: +$53,533. Negotiated PER work including Additional Services for SUE and meetings with Virginia Beach, Norfolk, and other stakeholders. |
| Design: | $580,000 | +55% | Delta: +$204,927. Incorporation of additional pipe condition assessment, hydraulic modeling for alternate pipe diameters, detailed traffic maintenance plans for both Norfolk and VA Beach. |
| Pre-Construction: | $21,000 | -71%  | Delta: -$50,442. Actual expenditures. |
| Construction: | $7,027,150 | +23% | Delta: +$1,311,750. Approved Change Orders of $30,000 (Owner Requested) and $70,000 (field changes). |
|  |  |  |  |
| Estimated Program Cost: | $7,878,150 | +21% | Delta: +$1,376,883.  |
| Contingency (5%): | $393,908 | -65% | Delta: -$749,172. Contingency held at 5%. |
| Estimated Project Cost: | $8,272,058 | +8% | Delta: +$627,711. |

**Updated Schedule:**

|  |  |  |  |
| --- | --- | --- | --- |
| Phase | Revised Schedule | % Change from CIP Baseline | Details |
| Pre-planning start: | July 2015 | 0% | Delta: +1 month from baseline date. |
| PER start: | December 2015 | 0% | Delta: +1 month from baseline date. Same duration as baseline between pre-planning and PER start. |
| Design start: | August 2016 | 0% | Delta: +1 month from baseline date. Same duration as baseline for PER phase. |
| Pre-Construction start: | October 2017 | -24% | Delta: -5 months from baseline date. One month added to Design duration evaluated at Final PER for total of 16 months for additional review times for Norfolk and Virginia Beach. |
| Construction start: | March 2018 | 0% | Delta: -5 months from baseline date. Same duration as baseline for pre-construction phase.  |
| Project Completion: | January 2020 | +10% | Delta: -4 months from baseline date. Duration is 2 months longer than the baseline Construction phase of 21 months due to Bid Document allowable duration + 30 day CO time extension. |

**Risk Assessment and Mitigation Discussion:**

|  |  |  |
| --- | --- | --- |
| Phase | Risk Assessment | Risk Mitigation Consideration |
| Pre-planning: | Closed out |  |
| PER: | Closed out |  |
| Design: | Closed out |  |
| Pre-Construction: | Closed out |  |
| Construction: | Likelihood of addition change orders for time extension and costs due to conflicts with undocumented private utilities along the force main corridor. | Evaluation of additional subsurface explorations ahead of Contractor’s installation crews to heighten efficiency. |
| Project Completion: | Issues discussed above may delay project completion. |  |

**Construction Closeout (February 1, 20209)**

**Updated Capital Budget:**

|  |  |  |  |
| --- | --- | --- | --- |
| Phase | Revised Costs | % Change from CIP Baseline | Details |
| Pre-planning: | $0 | -100% | Delta: -$142,885. The earlier anticipated costs for this phase were reassigned under Design. |
| PER: | $250,000 | +27% | Delta: +$53,533. Negotiated PER work including Additional Services for SUE and meetings with Virginia Beach, Norfolk, and other stakeholders. |
| Design: | $580,000 | +55% | Delta: +$204,927. Incorporation of additional pipe condition assessment, hydraulic modeling for alternate pipe diameters, detailed traffic maintenance plans for both Norfolk and VA Beach. |
| Pre-Construction: | $21,000 | -71%  | Delta: -$50,442. Actual expenditures. |
| Construction: | $7,127,150 | +25% | Delta: +$1,411,750. Additional approved Change Orders of $60,000 (field changes) plus additional $40,000 in CA/CI for approved time extension. |
|  |  |  |  |
| Estimated Program Cost: | $7,978,150 | +22% | Delta: +$1,476,883.  |
| Contingency (0%): | $0 | -100% | Delta: -$1,143.080. No contingencies. |
| Estimated Project Cost: | $7,978,150 | +4% | Delta: +$333,803. |

**Updated Schedule:**

|  |  |  |  |
| --- | --- | --- | --- |
| Phase | Revised Schedule | % Change from CIP Baseline | Details |
| Pre-planning start: | July 2015 | 0% | Delta: +1 month from baseline date. |
| PER start: | December 2015 | 0% | Delta: +1 month from baseline date. Same duration as baseline between pre-planning and PER start. |
| Design start: | August 2016 | 0% | Delta: +1 month from baseline date. Same duration as baseline for PER phase. |
| Pre-Construction start: | October 2017 | -24% | Delta: -5 months from baseline date. One month added to Design duration evaluated at Final PER for total of 16 months for additional review times for Norfolk and Virginia Beach. |
| Construction start: | March 2018 | 0% | Delta: -5 months from baseline date. Same duration as baseline for pre-construction phase.  |
| Project Completion: | February 2020 | +14% | Delta: -3 months from baseline date. Duration is 3 months longer than the baseline Construction phase of 21 months due to Bid Document allowable duration + 60 day CO time extension. |

**Risk Assessment and Mitigation Discussion:**

|  |  |  |
| --- | --- | --- |
| Phase | Risk Assessment | Risk Mitigation Consideration |
| Pre-planning: | Closed out |  |
| PER: | Closed out |  |
| Design: | Closed out |  |
| Pre-Construction: | Closed out |  |
| Construction: | Closed out |  |
| Project Completion: |  | Document and incorporate lessons learned for planned and future projects. |