## PER Schedule
Project Name
Project CIP Number
Project Phase | PER
Task Description | Duration (days) | Start | Finish | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01
Notice to Proceed | 1 | 2023-01-05 | 2023-01-06
Project Kickoff | 30 | 2023-01-06 | 2023-02-05 | bar: 2023-01-01
Alternatives Evaluation | 60 | 2023-02-05 | 2023-04-06 | bar: 2023-02-01 to 2023-03-01
Technical Memorandum Preparation | 30 | 2023-04-06 | 2023-05-06 | bar: 2023-04-01
HRSD Review Period | 30 | 2023-05-06 | 2023-06-05 | bar: 2023-05-01
Draft PER Preparation | 60 | 2023-06-05 | 2023-08-04 | bar: 2023-06-01 to 2023-07-01
HRSD Review Period | 30 | 2023-08-04 | 2023-09-03 | bar: 2023-08-01
Final PER Preparation and Submittal | 30 | 2023-09-03 | 2023-10-03 | bar: 2023-09-01
Formulas:
Finish = +[Start]+[Duration (days)]
Start = +[Finish, row above]

## Design Schedule
Project Name
Project CIP Number
Project Phase | Design
Task Description | Duration (days) | Start | Finish | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01
Notice to Proceed | 1 | 2023-01-05 | 2023-01-06
Survey / SUE / Geotechnical | 60 | 2023-01-06 | 2023-03-07 | bar: 2023-01-01 to 2023-02-01
Hydraulic Evaluation / Basis of Design | 30 | 2023-03-07 | 2023-04-06 | bar: 2023-03-01
50% Design Development | 60 | 2023-04-06 | 2023-06-05 | bar: 2023-04-01 to 2023-05-01
HRSD Review Period | 30 | 2023-06-05 | 2023-07-05 | bar: 2023-06-01
Review Draft Preconstruction Assesment | 15 | 2023-08-15 | 2023-09-01 | bar: 2023-08-01
90% Design Development | 60 | 2023-07-05 | 2023-09-03 | bar: 2023-07-01 to 2023-08-01
HRSD Review Period | 30 | 2023-09-03 | 2023-10-03 | bar: 2023-09-01
100% Design Development | 30 | 2023-10-03 | 2023-11-02 | bar: 2023-10-01
Review Final Preconstruction Assessment | 15 | 2023-10-15 | 2023-11-01 | bar: 2023-10-01
HRSD Review Period | 30 | 2023-11-02 | 2023-12-02 | bar: 2023-11-01
Bid Ready Plan Submittal | 30 | 2023-12-02 | 2024-01-01 | bar: 2023-12-01
Formulas:
Finish = +[Start]+[Duration (days)]
Start = +[Finish, row above]

## Pre-Construction Schedule
Project Name
Project CIP Number
Project Phase | Pre-Construction
Task Description | Duration (days) | Start | Finish | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01
Advertise for Construction Bids | 1 | 2023-01-05 | 2023-01-06
Site Visit / Issue Addendum | 30 | 2023-01-06 | 2023-02-05
Bid Opening | 1 | 2023-02-05 | 2023-02-06
Evaluation of Bids | 2 | 2023-02-06 | 2023-02-08
Commission Agenda Preparation | 21 | 2023-02-08 | 2023-03-01
Issue Notice of Award | 7 | 2023-03-01 | 2023-03-08
Issue Notice to Proceed | 30 | 2023-03-08 | 2023-04-07
Contractor Kickoff Meeting | 1 | 2023-04-07 | 2023-04-08 |  |  |  | #

## Construction Schedule
Project Name
Project CIP Number
Project Phase | Construction
Task Description | Duration (days) | Start | Finish | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01
Notice to Proceed | 1 | 2023-01-05 | 2023-01-06
Submittals Preparation, Review, Approval | 90 | 2023-01-06 | 2023-04-06 | bar: 2023-01-01 to 2023-03-01
Material/Equipment Order and Delivery | 90 | 2023-04-06 | 2023-07-05 | bar: 2023-04-01 to 2023-06-01
Mobilization / Site Clearing | 30 | 2023-07-05 | 2023-08-04 | bar: 2023-07-01
Site Work / Construction Activities | 120 | 2023-08-04 | 2023-12-02 | bar: 2023-08-01 to 2023-11-01
HRSD Involvement with Start-up & Testing | 30 | 2023-12-02 | 2024-01-01 | bar: 2023-12-01
Construction Activities for Substantial Completion Milestone | 60 | 2024-01-01 | 2024-03-01 | bar: 2024-01-01 to 2024-02-01
Substantial Completion Verifications (HRSD Assistance) | 30 | 2024-03-01 | 2024-03-31 | bar: 2024-03-01
Final Completion Verifications (HRSD Assistance) | 30 | 2024-03-31 | 2024-04-30 | bar: 2024-04-01
Project Closeout Stage | 60 | 2024-04-30 | 2024-06-29 | bar: 2024-05-01 to 2024-06-01
Formulas:
Finish = +[Start]+[Duration (days)]
Start = +[Finish, row above]