## Sheet1
Public Communication Program - Project Manager Checklist
Project Name:
Project Manager:
Design Engineer:
Use of Checklist: |  | This document is intended as an aide or "a trigger" to assist the project team to prepare and fulfill HRSD's Public Participation Program. It is not intended to replace any portion of the full Standards Section
Project Brief:
| × | not needed
| √ | required
Engage Locality Staff
Complete these items prior to meeting with HRSD Public Information Specialist |  |  | Completed
Obtain guidance from your Locality Partner for the following:
Identify localities single contact person and their contact information
Determine if Project Signs are required
Determine if City Council/Board of Supervisor Briefing is required (in person or written briefing)
Determine if an Open House is required - ask for City assistance with location and mailing list
Determine if VMBs (Variable Message Boards) will be required
Determine if there are Civic Leagues, residents, or businesses we should be aware of/address early
Determine City's additional PR requirements for this project (copy of notices, mailing lists)
Notes:
Identify Project Stakeholders
Completed
Stakeholder List - prepare and submit to Real Estate Manager and PM
Plan for Stakeholder Engagement
Notes:
Coordination with Project Team
Completed
Set meeting, if needed, to review expectations during project
Notes:
Public Open House/Community Meetings
Completed
Willingness to Hold
Public Meeting Advertisement
Open House Notice to the Public (mailed or door hung - does locality require copies?)
Public Meeting Prep/ Review
Determine/ Identify if a meeting with large stakeholders are necessary
Determine/ Identify other one-on-one meetings necessary
Schedule meetings with large stakeholders
Schedule other/additional Community or Business Leagues
Notes:
Project Notices & Updates
Completed
30 day Project Introduction Notice to all affected by the project
7 day Construction Notice
Additional Specialty Notices
Survey Notices
CCTV Notice
CCTV inspection and cleaning
Reminder Notices
Project Closeout Notice
Stakeholder Email with project page and subscription info
Notes:
Project Website
Completed
Is a Project Webpage needed-review timeline
Initial Project Upload Documents received by HRSD / uploaded to website
Review Monthly Update Process with Public Information Specialist
Notes:
Media Guidance / Prep (high profile projects)
Completed
Does the HRSD Project Manager request this service
Review HRSD's accepted procedures with consultant, inspector, contractor
Notes:
Project Closeout Checklist
Completed
Project Signs have been picked up and returned to HRSD - Public Information Specialist
Customer Inquiry Log has been finalized and closed out in Unifier
Project Closeout Notices have been sent to residents and businesses
Project Webpage has been updated to reflect a completed project and the approved HRSD thank you notice.
Notes: