## Cost & OPCC Report
Costs (*rounded to nearest $1,000)
Stage of Budget Estimate | AACE Cost Class | PER | Design | Bid Phase | Construction Administration | Construction Inspection | Construction | Closeout | Total
Initial Budget Development | 5 | [7 empty] | 0
Final PER | 4 | [7 empty] | 0
Preliminary Design | 3 | [7 empty] | 0
Pre-Final Design | 2 | [7 empty] | 0
Construction Bid Advertisement | 1 | [7 empty] | 0
Notes:
- Identify specific reasons for variance between each stage if total project cost changes by more than 10% and provide reasons in the same file as this Cost Report by phase.
- The stages called out above are a minimum requirement. Additional estimates may be added if appropriate. Make note of the current estimate with an asterisk (*).

## Schedule Report
Start Date by Phase
Stage of Schedule Estimate | PER | Design Delay | Design | Bid Delay | Bid Phase | Construction | Closeout
Initial Budget Development
Final PER
Preliminary Design
Pre-Final Design
Construction Bid Advertisement
Duration by Phase (numbers of months)
Stage of Schedule Estimate | PER | Design Delay | Design | Bid Delay | Bid Phase | Construction | Closeout | Total
Initial Budget Development | [7 empty] | 0
Final PER | [7 empty] | 0
Preliminary Design | [7 empty] | 0
Pre-Final Design | [7 empty] | 0
Construction Bid Advertisement | [7 empty] | 0
Notes:
- Identify specific reasons for schedule variance between each stage and provide reasons in the same file as this Schedule Report by phase.
- The stages called out above are a minimum requirement. Additional estimates may be added if appropriate. Make note of the current estimate with an asterisk (*).